## Joost
| Items in Checklist (Dutch) |  | possible comments | Items in Checklist (English) | Conditional Product (IFC) requirement for checklist | possible Defects
1 | Werkbezoek aan fabriek, eventueel meerdere bezoeken |  |  | Factory visits to inspect manufacturing,possible multiple visits | - | -
2 | Controle aanvoer kozijnen | 2a | packaging not intact | Check supplied frames during delivery | IF IfcWallStandardCase or IfcWall HAS IfcOpeningElement | Frames are damaged
|  | 2b | delivery not complete |  |  | Frame dimensions are incorrect
3 | Hebben de sparingen de juiste afmetingen (inclusief tolerentie)? | 3a | unsufficient tollerance | Do openings/recesses have the correct dimension with a tolerance of 10 mm? | IF IfcWallStandardCase or IfcWall HAS IfcOpeningElement | Openings dimensions are incorrect
|  | 3b | dimensions are not correct
|  | 3c | opening is not perpendicular
4 | Zitten de sparingen op de juiste plaats? | 4a | vertical position of opening not correct | Are the openings/recesses in the correct location? | IF IfcWallStandardCase or IfcWall HAS IfcOpeningElement | Opening locations are incorrect
|  | 4b | horizontal postion of opening not correct
5 | Controle bevestiging in het werk, niet aan buitenmetselwerk bevestigd |  |  | Check atachment of the work, not attached to outer masonry | IfcWindow OR IfcDoor
6 | Kozijnen en beglazing volledig afplakken | 6a | foil damaged | Full taping of window frames and glazing | IF IfcElement == IfcWindow OR IfcDoor (IF IfcWallStandardCase or IfcWall HAS IfcOpeningElement??) | Frames are not properly taped/protected
|  | 6b | foil missing
7 | Kwaliteit (let op beschadigingen) bij plaatsen | 7a | foil damaged | Quality during assembly (take note of damaged items) | IF IfcElement == IfcWindow OR IfcDoor (IF IfcWallStandardCase or IfcWall HAS IfcOpeningElement??) | Frames quality is poor due to workmanship
|  | 7b | glass damaged
|  | 7c | bottom sill damaged
|  | 7d | wooden frame damaged
|  | 7e | hinges and locks damaged
|  | 7f | vent damaged
8 | Kwaliteit (let op beschadigingen) bij oplevering | 8a | glass damaged | Quality during handover (take note of damaged items) | IF IfcElement == IfcWindow OR IfcDoor (IF IfcWallStandardCase or IfcWall HAS IfcOpeningElement??) | Frames quality is poor due to improper protection
|  | 8b | bottom sill damaged
|  | 8c | wooden frame damaged
|  | 8d | hinges and locks damaged
|  | 8e | vent damaged
|  | 8f | joints are not sealed correctly
|  | 8g | paint is not ok
|  | 8h | window is not clean
|  | 8i | window doens't open/close correctly |  |  | Frames quality is poor due to Supplier defect
9 | Zijn revisietekeningen gemaakt/noodzakelijk |  |  | Are drawing revisions necessary | - | -
10 | Zijn attesten aanwezig |  | yes / no | are test certificates available | - | -
11 | Binnenkozijnen schoongemaakt |  | not cleaned | Cleaning internal window/door frames | IF IfcWallStandardCase or IfcWall HAS IfcOpeningElement | Frames are damaged after removing tape and cleaning
Frames have paint stains/coloring after removing tape and cleaning